## Slide 1
Cyber Domain Status
Presentation to NBAC
Preston Werntz, CISA
Domain Steward Representative
21 October 2019

## Slide 2: Cyber Domain Status
Establishment of Domain Governance Structure and Procedures
Date | Activity
23 SEP 2019 | Leadership meeting between NIEM Management office and DHS/CISA
SEP 2019 | Identified Domain leadership including technical support staff for domain governance
26 SEP 2019 | Domain Nomination and Value Proposition presented to the NBAC
21 OCT 2019 | NBAC Vote/Recommendation to the ESC
OCT-DEC 2019 | Domain Charter and Domain Stewardship Agreement legal review
DEC 2019 | ESC Formal Endorsement of NIEM Cyber Domain

## Slide 3: Cyber Domain Status
Establishment of Domain Operations
Date | Activity
OCT-DEC 2019 | Identify potential use cases and scenarios
OCT-DEC 2019 | Gather Model Requirements and Identify Community Stakeholders
OCT-DEC 2019 | Identify relationships and dependencies with other Domains
NOV-DEC 2019 | Develop Terms of Reference for a Configuration Management Process (CMP) or Technical Review Board (TRB)
NOV-DEC 2019 | Develop communications and outreach plan
DEC 2019 | Identify training opportunities for leadership and supporting staff
DEC 2019 | Finalize Domain Charter and Domain Stewardship Agreement

## Slide 4: Cyber Domain Status
Domain Stand-Up
Date | Activity
JAN 2020 | Cyber Domain Kick-off Meeting
JAN 2020 | Continue development of proposed use cases and scenarios with Domain members
JAN-MAR 2020 | Establish Information Exchange Requirements (IER) from uses cases
JAN-MAR 2020 | Assess conversion of existing DHS/CISA Enterprise Conceptual Data Model – Cyber to NIEM conformant Model
MAR 2020 | Host NIEM Cyber Domain Symposium
MAR-MAY 2020 | Develop NIEM Cyber Domain Model with data components
MAY-JUL 2020 | Community Review of Domain Model
TBD | Publication of Domain Model

## Slide 5
Questions?